## Bug Report - 07th May
Bug ID | Bug Title | Bug Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Environment | Attachment | Date | Status | Assignee | Comment/Feedback | Reported By
BUG-001 | Login allows empty fields | The login form allows users to click the login button without entering email and password. No validation or warning message is displayed to the user. | 1. Open login page 2. Leave email and password fields empty 3. Click Login button | System should display validation messages for required fields. | Login request is processed without any validation. | High | High | QA/UAT Env | SS/Recorded Video | 07-May-2026 | Open | Relevant Dev | Any comment for this ticket will be maintain here. | Syed Ibtehaj - QA
BUG-002 | Invalid email accepted in signup | Signup form accepts invalid email format without showing any validation error. User is able to proceed with incorrect email structure. | 1. Open signup page 2. Enter invalid email like abc123 3. Fill remaining fields 4. Submit form | System should reject invalid email formats. | Form accepts invalid email input. | Medium | High | QA/UAT Env | SS/Recorded Video | 07-May-2026 | Open | Relevant Dev | Any comment for this ticket will be maintain here. | Syed Ibtehaj - QA
BUG-003 | Add to cart button not responding | When user clicks the Add to Cart button on product page, item is not added into cart and no response or loader appears. | 1. Open product page 2. Click Add to Cart button | Selected item should be added into shopping cart. | Button does not respond after click. | High | High | QA/UAT Env | SS/Recorded Video | 07-May-2026 | Open | Relevant Dev | Any comment for this ticket will be maintain here. | Syed Ibtehaj - QA
BUG-004 | Cart total price not updating | Cart total amount remains unchanged even after increasing or decreasing product quantity. | 1. Add product to cart 2. Increase quantity 3. Check total amount | Total amount should update automatically. | Cart total remains same. | Medium | Medium | QA/UAT Env | SS/Recorded Video | 07-May-2026 | In Progress | Relevant Dev | Any comment for this ticket will be maintain here. | Syed Ibtehaj - QA
BUG-005 | Broken homepage banner image | Homepage promotional banner image is not loading correctly and displays broken image icon. | 1. Open homepage 2. Observe homepage banner | Banner image should load properly. | Broken image icon displayed. | Low | Low | QA/UAT Env | SS/Recorded Video | 07-May-2026 | Open | Relevant Dev | Any comment for this ticket will be maintain here. | Syed Ibtehaj - QA
BUG-006 | Search shows unrelated results | Search functionality displays unrelated products for entered keywords, causing inaccurate search behavior. | 1. Search for 'Math Book' 2. Observe displayed results | Relevant books should appear according to keyword. | Unrelated books displayed. | Medium | Medium | QA/UAT Env | SS/Recorded Video | 07-May-2026 | Open | Relevant Dev | Any comment for this ticket will be maintain here. | Syed Ibtehaj - QA
BUG-007 | Checkout allows empty address | Checkout process allows user to continue without entering shipping address information. | 1. Add item to cart 2. Proceed to checkout 3. Leave address field empty 4. Click Continue | Validation should appear for mandatory address field. | Checkout proceeds without address. | High | High | QA/UAT Env | SS/Recorded Video | 07-May-2026 | Open | Relevant Dev | Any comment for this ticket will be maintain here. | Syed Ibtehaj - QA
BUG-008 | Payment successful with invalid card | System accepts invalid debit/credit card details and processes payment successfully without proper validation. | 1. Open payment page 2. Enter invalid card details 3. Click Pay Now | Payment should fail for invalid card details. | Payment processed successfully. | Critical | High | QA/UAT Env | SS/Recorded Video | 07-May-2026 | Open | Relevant Dev | Any comment for this ticket will be maintain here. | Syed Ibtehaj - QA